## Table 1
TENDER PROCESSING ESTIMATES LIST AS ON 19.12.2024
SL.No | Section | WBS No | Discription | Services Cost | Date of Payment | Payment Received
1 | Gadwal | 989000002883 | Providing of MS- Staircase for ERO Building in Gadwal Division of Gadwal Circle | 127370.94 | 04.12.2024
2 | K.T Doddy | T-2421-45-06-01-01-002 | Erection of 1No. 5MVA Addl. PTR on existing 1X5MVA PTR thus making total PTR capacity of 2X5MVA PTRs at 33/11KV Erkichedu SS in K.T. Doddy section in Gadwal circle under T&D PTR Augmentation Works (Summer Action Plan 2025). | 270468.12 | 12.12.2024
3 | Rajoli | T-2421-45-06-01-01-003 | Estimate for erection of 1No. 5MVA Addl. PTR to the existing 1X5MVA PTR thus making total PTR capacity of 2X5MVA PTRs at 33/11KV Rajoli Sub-Station in Rajoli section in Gadwal circle under T&D PTR Augmentation Works( Summer Action Plan 2025). | 313265.3 | 12.12.2024
4 | Aalmpur | T-2431-45-06-01-01-005 | Estimate for erection of 1.2 KM 33 KV interlinking line between 33/11 KV venkatapuram ss and 33 KV shanthinagar-I feeder to provide alternate source between 132/33 KV ieeza and 132/33 KV Alampur ss | 371085.46 | 17.12.2024
5 | Gadwal Town | T-2431-45-06-01-01-006 | Estimate for erection of 0.2 KM 33 KV line & 33 KV VCB at 132/33 KV SS Gadwal to provide alternate source to Gadwal new ss in Gadwal Town section | 177848.48 | 17.12.2024
6 | Ieeja | T-2431-45-06-01-01-003 | Estimate for erection of 1.56 KM Addl. 33 KV line for charging of new 33/11 KV SS Medikonda | 265446.02 | 18.12.2024

## T-2431-45-06-01-01-003
SCHEDULE
Name of the work: Erection of 1.56 KM Addl. 33 KV line for charging of new 33/11 KV SS Medikonda in Gadwal Circle . (WBS No. T-2431-45-06-01-01-003)
|  |  | Face Value |  | 265447
Sl No | Service Code | Description of work | Qty | Unit | Rates per Unit | Amount
1 | SWR10366 | Stringing 100sqmm 33/11kv Line 3 Cond SC | 1.56 | KM | 12600.06 | 19656.0936
2 | SWR11041 | Exc of Hard pit w/o blast 0.92X0.92X2.3M | 20 | EA | 1308.15 | 26163
3 | SWR10978 | Errection of 11 M long PSCC pole | 20 | EA | 4165.28 | 83305.6
4 | SMR11487 | S-MS Bolts & Nuts,Washers etc., | 60 | KG | 91.25 | 5475
5 | SWR11180 | SubTrnsprt 11M PSCC Pole incl. L&UL<10KM | 20 | EA | 431.97 | 8639.4
6 | SWR22092 | survey line&cabl inc peg mark&tree clear | 1.56 | KM | 765 | 1193.4
7 | SWR10466 | Formation of 33kvline vertical cutpoint | 2 | EA | 2908.02 | 5816.04
8 | SWR10378 | Numbering of poles incl. cost of paint | 20 | EA | 32 | 640
9 | SWR10294 | Cutting Charges for MS chanl 100x50mm | 10 | EA | 10 | 100
10 | SWR10308 | FABR-Drilling of holes upto 20 mm dia 5 | 30 | EA | 2 | 60
11 | SWR10393 | Erection of 11kv ABSwitch incl earthing | 1 | EA | 3200 | 3200
12 | SWR20308 | SubTrnsprt 9M PSCC Pole incl. L&UL<10KM | 29 | EA | 407.29 | 11811.41
13 | SWR11083 | Erec of 9.1 Mts PSCC poles for stuts | 15 | EA | 2400 | 36000
14 | SWR10343 | ERECTION OF LINES-Erection of 9.1M Pole | 14 | EA | 2400 | 33600
15 | SWR10107 | EXCAVATION OF PIT (2.6" x 2.6" x 6.0") | 29 | EA | 700 | 20300
16 | SWR10105 | EXCAVATION OF PIT (2.6" x 2.6" x 5.0') | 4 | EA | 600 | 2400
17 | SWR20307 | SubTrnsprt 8M PSCC Pole incl. L&UL<10KM | 4 | EA | 271.52 | 1086.08
18 | SWR21590 | Erection of 8.0Mts PSCC Poles for stuts | 4 | EA | 1500 | 6000
|  | GRAND TOTAL |  |  |  | 265446.0236
Conditions :
1 | The Contractor will have provide his own labour, T&P and Sub-Transport up to 10 km at his cost and above 10 km will be paid as per SSR.
2 | The required materials will be Supplied by the TGSPDCL on free of cost except which are not available matching materials in stores.
3 | The Contractor will be responsible for any accident to any of his workers and liability that may arise for payment of compensation under provision of act of A.P.
4 | The work shall be taken up strictly as per the Seniority and management instructions
5 | Agreement concluded with available SSR-2024-25 codes
6 | Agency which is excavating must use the CBUD App before commencing any excavation on public lands/roads in the state
Signature of the Contractor. |  |  |  | Superintending Engineer I/c
Operation Gadwal.
COMPARATIVE STATEMENT
The Rates quoted by M/s Vijetha Electrical Constructions, Wanaparthy Has Quoted lowest rates. Hence accepted.
Sl No | Service Code | Description of work | Qty | Unit | SSR Rates per Unit
The Rates quoted by Mr. Ravendra Goud, Contractor, K.R.Cheruvu has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Sreenivasa Goud, Contractor, Shanthinagar has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. E.Nagendra, Contractor, Kurnool has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Vijetha Electricals, Contractor, Wanaparthy has quoted lowest rates. Hence accepted.
The Rates quoted by M/s Harika Electricals, Contractor, Ieeza has quoted lowest rates. Hence accepted.
The Rates quoted by Mr. Praveen Kumar, Contractor, Gadwal has quoted lowest rates. Hence accepted.
| Rates quoted by the Contractor | Amount quoted by the Contractor
Sub-Total:
12.36 % Service tax: | [5 empty] | 0
Total: | [5 empty] | 0
Sri Raghavendra Goud, Civil & Electrical contractor, H. No. 2-21, K.R Cheruvu, Maldakal
Sri E.Nagendra, Contractor, Electrical & Civil Works, H. No. 40-310A, Bhagyanagar, Kurnool
M/s Vijetha Electrical Constructions, H. No. 42-187/6, Vengalrao Colony, Wanaparthy
Sri S.E.Sreenivasa Goud, Contractor, Electrical&Civil Works, Shanthinagar vg., Waddepally M